## Progress chart
Progress Chart
|  | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
Tower -1 | Planned | bar: 2024-06-01 to 2025-03-01
20# | Tender | bar: 2024-11-01 to 2025-02-01
Actual
Tower -2 | Planned | bar: 2024-07-01 to 2025-04-01
20# | Tender | bar: 2024-12-01 to 2025-03-01
Actual
Tower -3 | Planned | bar: 2024-08-01 to 2025-05-01
20# | Tender | bar: 2025-01-01 to 2025-04-01
Actual
Tower -4 | Planned | bar: 2024-09-01 to 2025-06-01
20# | Tender | bar: 2025-02-01 to 2025-05-01
Actual
Tower -5 | Planned | bar: 2024-10-01 to 2025-07-01
20# | Tender | bar: 2025-03-01 to 2025-06-01
Actual
Tower -6 | Planned | bar: 2024-11-01 to 2025-08-01
20# | Tender | bar: 2025-04-01 to 2025-07-01
Actual
Infra -1 | Planned | bar: 2024-06-01 to 2025-03-01
20# | Tender | bar: 2024-11-01 to 2025-02-01
Actual
MLCP | Planned | bar: 2024-06-01 to 2025-03-01
20# | Tender | bar: 2024-11-01 to 2025-02-01
Actual
Concept
Scheme
Detail design
VFC
Tender

## For Sale with predecessor (hidden)
Design Delivery Schedule for New Project | New Project - | [7 empty] | New Project - | [7 empty] | New Project - | [7 empty] | New Project - | [7 empty] | New Project - | [7 empty] | New Project -
Buildings DDS | Internal Release |  |  |  | External Release |  |  |  | Internal Release |  |  |  | External Release |  |  |  | Internal Release |  |  |  | External Release |  |  |  | Internal Release |  |  |  | External Release |  |  |  | Internal Release |  |  |  | External Release |  |  |  | Internal Release |  |  |  | External Release
Building Name | As per Policy (no of weeks from Concept | As per Current Progress (no of weeks from Preceding Deliverable)(+sucessor/-predecessor) | As Per Policy | Actual Expected | As per Policy (no of weeks from Concept | As per Current Progress (no of weeks from Preceding Deliverable)(+sucessor/-predecessor) | As Per Policy | Actual Expected | As per Policy (no of weeks from Concept | As per Current Progress (no of weeks from Preceding Deliverable)(+sucessor/-predecessor) | As Per Policy | Actual Expected | As per Policy (no of weeks from Concept | As per Current Progress (no of weeks from Preceding Deliverable)(+sucessor/-predecessor) | As Per Policy | Actual Expected | As per Policy (no of weeks from Concept | As per Current Progress (no of weeks from Preceding Deliverable)(+sucessor/-predecessor) | As Per Policy | Actual Expected | As per Policy (no of weeks from Concept | As per Current Progress (no of weeks from Preceding Deliverable)(+sucessor/-predecessor) | As Per Policy | Actual Expected | As per Policy (no of weeks from Concept | As per Current Progress (no of weeks from Preceding Deliverable)(+sucessor/-predecessor) | As Per Policy | Actual Expected | As per Policy (no of weeks from Concept | As per Current Progress (no of weeks from Preceding Deliverable)(+sucessor/-predecessor) | As Per Policy | Actual Expected | As per Policy (no of weeks from Concept | As per Current Progress (no of weeks from Preceding Deliverable)(+sucessor/-predecessor) | As Per Policy | Actual Expected | As per Policy (no of weeks from Concept | As per Current Progress (no of weeks from Preceding Deliverable)(+sucessor/-predecessor) | As Per Policy | Actual Expected | As per Policy (no of weeks from Concept | As per Current Progress (no of weeks from Preceding Deliverable)(+sucessor/-predecessor) | As Per Policy | Actual Expected | As per Policy (no of weeks from Concept | As per Current Progress (no of weeks from Preceding Deliverable)(+sucessor/-predecessor) | As Per Policy | Actual Expected | Link
Typology |  |  | For sale | For sale |  |  | For sale | For sale |  |  | For sale | For sale |  |  | For sale | For sale |  |  | For sale | For sale |  |  | For sale | For sale |  |  | For sale | For sale |  |  | For sale | For sale |  |  | For sale | For sale |  |  | For sale | For sale |  |  | For sale | For sale |  |  | For sale | For sale
Building Height |  |  | <30m | <30m |  |  | <30m | <30m |  |  | <= 30-50 m | <= 30-50 m |  |  | <= 30-50 m | <= 30-50 m |  |  | 50-70 m | 50-70 m |  |  | 50-70 m | 50-70 m |  |  | 70-100 m | 70-100 m |  |  | 70-100 m | 70-100 m |  |  | 100-150 m | 100-150 m |  |  | 100-150 m | 100-150 m |  |  | 150 m+ | 150 m+ |  |  | 150 m+ | 150 m+
Building Configuration
Project Start Date (Email from AML) | 0 |  | 2015-09-08 | 2015-09-08 | 0 |  | 2015-09-08 | 2015-09-08 | 0 |  | 2015-09-08 | 2015-09-08 | 0 |  | 2015-09-08 | 2015-09-08 | 0 |  | 2015-09-08 | 2015-09-08 | 0 |  | 2015-09-08 | 2015-09-08 | 0 |  | 2015-09-08 | 2015-09-08 | 0 |  | 2015-09-08 | 2015-09-08 | 0 |  | 2015-09-08 | 2015-09-08 | 0 |  | 2015-09-08 | 2015-09-08 | 0 |  | 2015-09-08 | 2015-09-08 | 0 |  | 2015-09-08 | 2015-09-08
Concept Finalization | 12 | 12 | 2015-12-01 | 2015-12-01 | 12 | 12 | 2015-12-01 | 2015-12-01 | 12 | 12 | 2015-12-01 | 2015-12-01 | 12 | 12 | 2015-12-01 | 2015-12-01 | 12 | 12 | 2015-12-01 | 2015-12-01 | 12 | 12 | 2015-12-01 | 2015-12-01 | 12 | 12 | 2015-12-01 | 2015-12-01 | 12 | 12 | 2015-12-01 | 2015-12-01 | 12 | 12 | 2015-12-01 | 2015-12-01 | 12 | 12 | 2015-12-01 | 2015-12-01 | 12 | 12 | 2015-12-01 | 2015-12-01 | 12 | 12 | 2015-12-01 | 2015-12-01
Excavation Tender & VFC (upto 1 m above final depth) |  |  |  |  | 2 | 2 | 2015-12-15 | 2015-12-15 |  |  |  |  | 2 | 2 | 2015-12-15 | 2015-12-15 |  |  |  |  | 2 | 2 | 2015-12-15 | 2015-12-15 |  |  |  |  | 3 | 3 | 2015-12-22 | 2015-12-22 |  |  |  |  | 4 | 4 | 2015-12-29 | 2015-12-29 |  |  |  |  | 4 | 4 | 2015-12-29 | 2015-12-29
Civil Tender |  |  |  |  | 6 | 3 | 2016-01-12 | 2016-01-12 |  |  |  |  | 6 | 3 | 2016-01-12 | 2016-01-12 |  |  |  |  | 6 | 3 | 2016-01-12 | 2016-01-12 |  |  |  |  | 8 | 4 | 2016-01-26 | 2016-01-26 |  |  |  |  | 12 | 6 | 2016-02-23 | 2016-02-23 |  |  |  |  | 12 | 4 | 2016-02-23 | 2016-02-23 | ROW11
- Civil Schematic2 | 3 | 1 | 2015-12-22 | 2015-12-22 |  |  |  |  | 3 | 1 | 2015-12-22 | 2015-12-22 |  |  |  |  | 3 | 1 | 2015-12-22 | 2015-12-22 |  |  |  |  | 4 | 1 | 2015-12-29 | 2015-12-29 |  |  |  |  | 6 | 2 | 2016-01-12 | 2016-01-12 |  |  |  |  | 8 | 4 | 2016-01-26 | 2016-01-26 |  |  |  |  | ROW9
- MEP Schematic | 3 | 1 | 2015-12-22 | 2015-12-22 |  |  |  |  | 3 | 1 | 2015-12-22 | 2015-12-22 |  |  |  |  | 3 | 1 | 2015-12-22 | 2015-12-22 |  |  |  |  | 4 | 1 | 2015-12-29 | 2015-12-29 |  |  |  |  | 6 | 2 | 2016-01-12 | 2016-01-12 |  |  |  |  | 8 | 4 | 2016-01-26 | 2016-01-26 |  |  |  |  | ROW9
Shoring Tender & VFC + final (upto) 1 m excavation |  |  |  |  | 10 | 4 | 2016-02-09 | 2016-02-09 |  |  |  |  | 10 | 4 | 2016-02-09 | 2016-02-09 | 10 |  |  |  | 10 | 4 | 2016-02-09 | 2016-02-09 |  |  |  |  | 12 | 4 | 2016-02-23 | 2016-02-23 |  |  |  |  | 12 | 0 | 2016-02-23 | 2016-02-23 |  |  |  |  | 12 | 0 | 2016-02-23 | 2016-02-23
Raft/Piling/Foundation VFC |  |  |  |  | 14 | 4 | 2016-03-08 | 2016-03-08 |  |  |  |  | 14 | 4 | 2016-03-08 | 2016-03-08 |  |  |  |  | 14 | 4 | 2016-03-08 | 2016-03-08 |  |  |  |  | 16 | 4 | 2016-03-22 | 2016-03-22 |  |  |  |  | 22 | 6 | 2016-05-03 | 2016-05-03 |  |  |  |  | 24 | 4 | 2016-05-17 | 2016-05-17 | ROW15
- Coordinated GA3 for Foundation | 10 | 0 | 2016-02-09 | 2016-02-09 |  |  |  |  | 10 | 0 | 2016-02-09 | 2016-02-09 |  |  |  |  | 10 | 0 | 2016-02-09 | 2016-02-09 |  |  |  |  | 12 | 0 | 2016-02-23 | 2016-02-23 |  |  |  |  | 16 | 4 | 2016-03-22 | 2016-03-22 |  |  |  |  | 20 | 4 | 2016-04-19 | 2016-04-19 |  |  |  |  | ROW16
- Wind tunnel test report | NA | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | NA | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | NA | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | NA | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | 12 | 0 | 2016-02-23 | 2016-02-23 |  |  |  |  | 16 | 4 | 2016-03-22 | 2016-03-22 |  |  |  |  | ROW13
MEP VFC IFC (Input for Construction) |  |  |  |  | 16 | 2 | 2016-03-22 | 2016-03-22 |  |  |  |  | 16 | 2 | 2016-03-22 | 2016-03-22 |  |  |  |  | 16 | 2 | 2016-03-22 | 2016-03-22 |  |  |  |  | 20 | 4 | 2016-04-19 | 2016-04-19 |  |  |  |  | 26 | 4 | 2016-05-31 | 2016-05-31 |  |  |  |  | 28 | 4 | 2016-06-14 | 2016-06-14 | ROW14
Issue of Formwork GA set to vendor/contractor |  |  |  |  | NA | NA | #VALUE! | #VALUE! |  |  |  |  | NA | NA | #VALUE! | #VALUE! | 16 |  |  |  | 16 | 2 | 2016-03-22 | 2016-03-22 |  |  |  |  | 18 | 2 | 2016-04-05 | 2016-04-05 |  |  |  |  | 24 | 2 | 2016-05-17 | 2016-05-17 |  |  |  |  | 26 | 2 | 2016-05-31 | 2016-05-31 | ROW14
Finalization of Forwork GA set by vendor/contractor |  |  |  |  | NA | NA | #VALUE! | #VALUE! |  |  |  |  | NA | NA | #VALUE! | #VALUE! | 20 |  |  |  | 20 | 4 | 2016-04-19 | 2016-04-19 |  |  |  |  | 24 | 6 | 2016-05-17 | 2016-05-17 |  |  |  |  | 30 | 6 | 2016-06-28 | 2016-06-28 |  |  |  |  | 32 | 6 | 2016-07-12 | 2016-07-12 | ROW18
Structural VFC upto Ground* |  |  |  |  | 18 | 2 | 2016-04-05 | 2016-04-05 |  |  |  |  | 18 | 2 | 2016-04-05 | 2016-04-05 |  |  |  |  | 18 | 2 | 2016-04-05 | 2016-04-05 |  |  |  |  | 24 | 2 | 2016-05-17 | 2016-05-17 |  |  |  |  | 30 | 2 | 2016-06-28 | 2016-06-28 |  |  |  |  | 32 | 2 | 2016-07-12 | 2016-07-12 | ROW23
- Coordinated GA3 upto Ground | 10 | -4 | 2016-02-09 | 2016-02-09 |  |  |  |  | 10 | -4 | 2016-02-09 | 2016-02-09 |  |  |  |  | 13 | -1 | 2016-03-01 | 2016-03-01 |  |  |  |  | 15 | -1 | 2016-03-15 | 2016-03-15 |  |  |  |  | 22 | 0 | 2016-05-03 | 2016-05-03 |  |  |  |  | 22 | -2 | 2016-05-03 | 2016-05-03 |  |  |  |  | ROW14
- Structural VFC4 (Internal) | 14 | 4 | 2016-03-08 | 2016-03-08 |  |  |  |  | 14 | 4 | 2016-03-08 | 2016-03-08 |  |  |  |  | 14 | 1 | 2016-03-08 | 2016-03-08 |  |  |  |  | 20 | 5 | 2016-04-19 | 2016-04-19 |  |  |  |  | 26 | 4 | 2016-05-31 | 2016-05-31 |  |  |  |  | 26 | 4 | 2016-05-31 | 2016-05-31 |  |  |  |  | ROW21
- MEP IFC6 | 16 | 2 | 2016-03-22 | 2016-03-22 |  |  |  |  | 16 | 2 | 2016-03-22 | 2016-03-22 |  |  |  |  | 16 | 2 | 2016-03-22 | 2016-03-22 |  |  |  |  | 22 | 2 | 2016-05-03 | 2016-05-03 |  |  |  |  | 28 | 2 | 2016-06-14 | 2016-06-14 |  |  |  |  | 30 | 4 | 2016-06-28 | 2016-06-28 |  |  |  |  | ROW22
MEP VFC IFC (Input for Construction) |  |  |  |  | 20 | 2 | 2016-04-19 | 2016-04-19 |  |  |  |  | 20 | 2 | 2016-04-19 | 2016-04-19 |  |  |  |  | 20 | 2 | 2016-04-19 | 2016-04-19 |  |  |  |  | 28 | 4 | 2016-06-14 | 2016-06-14 |  |  |  |  | 34 | 4 | 2016-07-26 | 2016-07-26 |  |  |  |  | 38 | 6 | 2016-08-23 | 2016-08-23 | ROW20
Structural VFC for first 5-10 floors above ground** |  |  |  |  | 22 | 4 | 2016-05-03 | 2016-05-03 |  |  |  |  | 24 | 4 | 2016-05-17 | 2016-05-17 |  |  |  |  | 26 | 4 | 2016-05-31 | 2016-05-31 |  |  |  |  | 32 | 4 | 2016-07-12 | 2016-07-12 |  |  |  |  | 38 | 4 | 2016-08-23 | 2016-08-23 |  |  |  |  | 40 | 4 | 2016-09-06 | 2016-09-06 | ROW31
- Facade Cast-in Details | 16 | -2 | 2016-03-22 | 2016-03-22 |  |  |  |  | 18 | 0 | 2016-04-05 | 2016-04-05 |  |  |  |  | 20 | 2 | 2016-04-19 | 2016-04-19 |  |  |  |  | 26 | 2 | 2016-05-31 | 2016-05-31 |  |  |  |  | 30 | 0 | 2016-06-28 | 2016-06-28 |  |  |  |  | 34 | 2 | 2016-07-26 | 2016-07-26 |  |  |  |  | ROW20
- Coordinated GA3for first 5-10 floors above ground | 16 | -2 | 2016-03-22 | 2016-03-22 |  |  |  |  | 18 | 0 | 2016-04-05 | 2016-04-05 |  |  |  |  | 20 | 2 | 2016-04-19 | 2016-04-19 |  |  |  |  | 26 | 2 | 2016-05-31 | 2016-05-31 |  |  |  |  | 32 | 2 | 2016-07-12 | 2016-07-12 |  |  |  |  | 36 | 4 | 2016-08-09 | 2016-08-09 |  |  |  |  | ROW20
- Structural VFC4 (Internal) | 18 | 2 | 2016-04-05 | 2016-04-05 |  |  |  |  | 20 | 2 | 2016-04-19 | 2016-04-19 |  |  |  |  | 22 | 2 | 2016-05-03 | 2016-05-03 |  |  |  |  | 28 | 2 | 2016-06-14 | 2016-06-14 |  |  |  |  | 34 | 2 | 2016-07-26 | 2016-07-26 |  |  |  |  | 38 | 2 | 2016-08-23 | 2016-08-23 |  |  |  |  | ROW27
- ID Concept Finalization7,8 | 18 | 0 | 2016-04-05 | 2016-04-05 |  |  |  |  | 20 | 0 | 2016-04-19 | 2016-04-19 |  |  |  |  | 22 | 0 | 2016-05-03 | 2016-05-03 |  |  |  |  | 28 | 0 | 2016-06-14 | 2016-06-14 |  |  |  |  | 32 | -2 | 2016-07-12 | 2016-07-12 |  |  |  |  | 36 | -2 | 2016-08-09 | 2016-08-09 |  |  |  |  | ROW28
- MEP IFC6 | 20 | 2 | 2016-04-19 | 2016-04-19 |  |  |  |  | 22 | 2 | 2016-05-03 | 2016-05-03 |  |  |  |  | 24 | 2 | 2016-05-17 | 2016-05-17 |  |  |  |  | 30 | 2 | 2016-06-28 | 2016-06-28 |  |  |  |  | 36 | 4 | 2016-08-09 | 2016-08-09 |  |  |  |  | 40 | 4 | 2016-09-06 | 2016-09-06 |  |  |  |  | ROW29
- Civil DD for Entire Building | 18 | -2 | 2016-04-05 | 2016-04-05 |  |  |  |  | 20 | -2 | 2016-04-19 | 2016-04-19 |  |  |  |  | 22 | -2 | 2016-05-03 | 2016-05-03 |  |  |  |  | 28 | -2 | 2016-06-14 | 2016-06-14 |  |  |  |  | 34 | -2 | 2016-07-26 | 2016-07-26 |  |  |  |  | 36 | -4 | 2016-08-09 | 2016-08-09 |  |  |  |  | ROW30
MEP VFC IFC (Input for Construction) |  |  |  |  | 24 | 2 | 2016-05-17 | 2016-05-17 |  |  |  |  | 26 | 2 | 2016-05-31 | 2016-05-31 |  |  |  |  | 28 | 2 | 2016-06-14 | 2016-06-14 |  |  |  |  | 36 | 4 | 2016-08-09 | 2016-08-09 |  |  |  |  | 42 | 4 | 2016-09-20 | 2016-09-20 |  |  |  |  | 46 | 6 | 2016-10-18 | 2016-10-18 | ROW25
Structural VFC for balance structure (100%)*** |  |  |  |  | NA | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | 28 | 2 | 2016-06-14 | 2016-06-14 |  |  |  |  | 32 | 2 | 2016-07-12 | 2016-07-12 |  |  |  |  | 48 | 2 | 2016-11-01 | 2016-11-01 |  |  |  |  | 54 | 2 | 2016-12-13 | 2016-12-13 |  |  |  |  | 64 | 4 | 2017-02-21 | 2017-02-21 | ROW37
- Coordinated GA3 for balance structure (100%) | NA | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | 22 | -2 | 2016-05-03 | 2016-05-03 |  |  |  |  | 26 | 0 | 2016-05-31 | 2016-05-31 |  |  |  |  | 40 | 8 | 2016-09-06 | 2016-09-06 |  |  |  |  | 46 | 8 | 2016-10-18 | 2016-10-18 |  |  |  |  | 54 | 14 | 2016-12-13 | 2016-12-13 |  |  |  |  | ROW25
- Structural VFC4 (Internal) | NA | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | 24 | 2 | 2016-05-17 | 2016-05-17 |  |  |  |  | 28 | 2 | 2016-06-14 | 2016-06-14 |  |  |  |  | 42 | 2 | 2016-09-20 | 2016-09-20 |  |  |  |  | 48 | 2 | 2016-11-01 | 2016-11-01 |  |  |  |  | 56 | 2 | 2016-12-27 | 2016-12-27 |  |  |  |  | ROW34
- MEP IFC6 | NA | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | 26 | 2 | 2016-05-31 | 2016-05-31 |  |  |  |  | 30 | 2 | 2016-06-28 | 2016-06-28 |  |  |  |  | 46 | 4 | 2016-10-18 | 2016-10-18 |  |  |  |  | 52 | 4 | 2016-11-29 | 2016-11-29 |  |  |  |  | 62 | 6 | 2017-02-07 | 2017-02-07 |  |  |  |  | ROW35
- Civil DD for balance Structure (100%) | NA | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | 26 | 0 | 2016-05-31 | 2016-05-31 |  |  |  |  | 30 | 0 | 2016-06-28 | 2016-06-28 |  |  |  |  | 46 | 0 | 2016-10-18 | 2016-10-18 |  |  |  |  | 52 | 0 | 2016-11-29 | 2016-11-29 |  |  |  |  | 60 | -2 | 2017-01-24 | 2017-01-24 |  |  |  |  | ROW36
MEP VFC IFC (Input for Construction) |  |  |  |  | NA | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | 30 | 2 | 2016-06-28 | 2016-06-28 |  |  |  |  | 34 | 2 | 2016-07-26 | 2016-07-26 |  |  |  |  | 52 | 4 | 2016-11-29 | 2016-11-29 |  |  |  |  | 58 | 4 | 2017-01-10 | 2017-01-10 |  |  |  |  | 68 | 4 | 2017-03-21 | 2017-03-21 | ROW33
Facade tender (including windows and external painting) |  |  |  |  | 30 | 8 | 2016-06-28 | 2016-06-28 |  |  |  |  | 36 | 8 | 2016-08-09 | 2016-08-09 |  |  |  |  | 40 | 8 | 2016-09-06 | 2016-09-06 |  |  |  |  | 44 | -4 | 2016-10-04 | 2016-10-04 |  |  |  |  | 52 | -2 | 2016-11-29 | 2016-11-29 |  |  |  |  | 52 | -12 | 2016-11-29 | 2016-11-29 | ROW33
Facade mockup / Testing (for high rise and super high rise only) |  |  |  |  | NA | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | NA | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | NA | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | 74 | 26 | 2017-05-02 | 2017-05-02 |  |  |  |  | 82 | 28 | 2017-06-27 | 2017-06-27 |  |  |  |  | 82 | 18 | 2017-06-27 | 2017-06-27 | ROW33
MEP Tender |  |  |  |  | 38 | 2 | 2016-08-23 | 2016-08-23 |  |  |  |  | 42 | 2 | 2016-09-20 | 2016-09-20 |  |  |  |  | 58 | 2 | 2017-01-10 | 2017-01-10 |  |  |  |  | 71 | 2 | 2017-04-11 | 2017-04-11 |  |  |  |  | 82 | 2 | 2017-06-27 | 2017-06-27 |  |  |  |  | 92 | 2 | 2017-09-05 | 2017-09-05 | ROW48
Fitouts Tender |  |  |  |  | 38 | 4 | 2016-08-23 | 2016-08-23 |  |  |  |  | 42 | 4 | 2016-09-20 | 2016-09-20 |  |  |  |  | 58 | 4 | 2017-01-10 | 2017-01-10 |  |  |  |  | 71 | 4 | 2017-04-11 | 2017-04-11 |  |  |  |  | 82 | 4 | 2017-06-27 | 2017-06-27 |  |  |  |  | 92 | 4 | 2017-09-05 | 2017-09-05 | ROW47
Lifts Tender |  |  |  |  | 38 | 0 | 2016-08-23 | 2016-08-23 |  |  |  |  | 42 | 0 | 2016-09-20 | 2016-09-20 |  |  |  |  | 58 | 0 | 2017-01-10 | 2017-01-10 |  |  |  |  | 71 | 0 | 2017-04-11 | 2017-04-11 |  |  |  |  | 82 | 0 | 2017-06-27 | 2017-06-27 |  |  |  |  | 92 | 0 | 2017-09-05 | 2017-09-05 | ROW41
BMS & Security System Tender |  |  |  |  | 38 | 0 | 2016-08-23 | 2016-08-23 |  |  |  |  | 46 | 4 | 2016-10-18 | 2016-10-18 |  |  |  |  | 72 | 14 | 2017-04-18 | 2017-04-18 |  |  |  |  | 83 | 12 | 2017-07-04 | 2017-07-04 |  |  |  |  | 92 | 10 | 2017-09-05 | 2017-09-05 |  |  |  |  | 92 | 0 | 2017-09-05 | 2017-09-05 | ROW41
All other tenders related to the building |  |  |  |  | 38 | 0 | 2016-08-23 | 2016-08-23 |  |  |  |  | 46 | 4 | 2016-10-18 | 2016-10-18 |  |  |  |  | 72 | 14 | 2017-04-18 | 2017-04-18 |  |  |  |  | 83 | 12 | 2017-07-04 | 2017-07-04 |  |  |  |  | 92 | 10 | 2017-09-05 | 2017-09-05 |  |  |  |  | 92 | 0 | 2017-09-05 | 2017-09-05 | ROW41
MEP VFC |  |  |  |  | 46 | [7 empty] | 50 | [7 empty] | 66 | [7 empty] | NA | [7 empty] | NA
Fitouts VFC |  |  |  |  | 34 | 10 | 2016-07-26 | 2016-07-26 |  |  |  |  | 38 | 8 | 2016-08-23 | 2016-08-23 |  |  |  |  | 54 | 20 | 2016-12-13 | 2016-12-13 |  |  |  |  | 67 | 15 | 2017-03-14 | 2017-03-14 |  |  |  |  | 78 | 20 | 2017-05-30 | 2017-05-30 |  |  |  |  | 88 | 20 | 2017-08-08 | 2017-08-08 | ROW38
MEP VFC For Fitouts |  |  |  |  | 36 | 2 | 2016-08-09 | 2016-08-09 |  |  |  |  | 40 | 2 | 2016-09-06 | 2016-09-06 |  |  |  |  | 56 | 2 | 2016-12-27 | 2016-12-27 |  |  |  |  | 69 | 2 | 2017-03-28 | 2017-03-28 |  |  |  |  | 80 | 2 | 2017-06-13 | 2017-06-13 |  |  |  |  | 90 | 2 | 2017-08-22 | 2017-08-22 | ROW47
VFC for all other tenders related to the building |  |  |  |  | 46 | 8 | 2016-10-18 | 2016-10-18 |  |  |  |  | 50 | 8 | 2016-11-15 | 2016-11-15 |  |  |  |  | 60 | 2 | 2017-01-24 | 2017-01-24 |  |  |  |  | 68 | -3 | 2017-03-21 | 2017-03-21 |  |  |  |  | 80 | -2 | 2017-06-13 | 2017-06-13 |  |  |  |  | 88 | -4 | 2017-08-08 | 2017-08-08 | ROW41
100% MEP Shop Drawings (part interim approvals shall be done) |  |  |  |  | NA | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | NA | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | NA | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | 88 | 19 | 2017-08-08 | 2017-08-08 |  |  |  |  | 102 | 22 | 2017-11-14 | 2017-11-14 |  |  |  |  | 116 | 26 | 2018-02-20 | 2018-02-20 | ROW48
Completion |  |  |  |  | 95 | #VALUE! | 2017-09-26 | #VALUE! |  |  |  |  | 101 | #VALUE! | 2017-11-07 | #VALUE! |  |  |  |  | 122 | #VALUE! | 2018-04-03 | #VALUE! |  |  |  |  | 135 | 47 | 2018-07-03 | 2018-07-03 |  |  |  |  | 162 | 60 | 2019-01-08 | 2019-01-08 |  |  |  |  | 206 | 90 | 2019-11-12 | 2019-11-12 | ROW50

## T1-T6+Infra+MLCP
Design Delivery Schedule for New Project | New Project - Bhandup Neptune
Buildings DDS | DATES AS PER DDS POLICY
Building Name - T1, T2, T3, T4, T5, T6 | Policy # of Weeks | RESI | RESI | RESI | RESI | RESI | RESI
Typology - 2 BHK, 2.5 BHK, 3 BHK |  | Sale Tower | Sale Tower | Sale Tower | Sale Tower | Sale Tower | Sale Tower
Building Height - 135.45 M
Building Configuration |  | T1 | T2 | T3 | T4 | T5 | T6
Project Start Date (Email from AML) | 0 | 2024-06-26
Concept Finalization | 12 | 2024-09-18
Excavation Tender & VFC (upto 1 m above final depth) | 3 | 2024-10-09 | 2024-11-06 | 2024-12-04 | 2025-01-01 | 2025-01-29 | 2025-02-26
Civil Tender | 8 | 2024-11-13 | 2024-12-11 | 2025-01-08 | 2025-02-05 | 2025-03-05 | 2025-04-02
- Civil Schematic2 | 4 | 2024-10-16 | 2024-11-13 | 2024-12-11 | 2025-01-08 | 2025-02-05 | 2025-03-05
- MEP Schematic | 4 | 2024-10-16 | 2024-11-13 | 2024-12-11 | 2025-01-08 | 2025-02-05 | 2025-03-05
Shoring Tender & VFC + final (upto) 1 m excavation | 12 | 2024-12-11 | 2025-01-08 | 2025-02-05 | 2025-03-05 | 2025-04-02 | 2025-04-30
Raft/Piling/Foundation VFC | 16 | 2025-01-08 | 2025-02-05 | 2025-03-05 | 2025-04-02 | 2025-04-30 | 2025-05-28
- Coordinated GA3 for Foundation | 12 | 2024-12-11 | 2025-01-08 | 2025-02-05 | 2025-03-05 | 2025-04-02 | 2025-04-30
- Wind tunnel test report | NA
MEP VFC IFC (Input for Construction) | 20 | 2025-02-05 | 2025-03-05 | 2025-04-02 | 2025-04-30 | 2025-05-28 | 2025-06-25
Issue of Formwork GA set to vendor/contractor | 18 | 2025-01-22 | 2025-02-19 | 2025-03-19 | 2025-04-16 | 2025-05-14 | 2025-06-11
Finalization of Forwork GA set by vendor/contractor | 24 | 2025-03-05 | 2025-04-02 | 2025-04-30 | 2025-05-28 | 2025-06-25 | 2025-07-23
Structural VFC upto Ground* | 24 | 2025-03-05 | 2025-04-02 | 2025-04-30 | 2025-05-28 | 2025-06-25 | 2025-07-23
- Coordinated GA3 upto Ground | 15 | 2025-01-01 | 2025-01-29 | 2025-02-26 | 2025-03-26 | 2025-04-23 | 2025-05-21
- Structural VFC4 (Internal) | 20 | 2025-02-05 | 2025-03-05 | 2025-04-02 | 2025-04-30 | 2025-05-28 | 2025-06-25
- MEP IFC6 | 22 | 2025-02-19 | 2025-03-19 | 2025-04-16 | 2025-05-14 | 2025-06-11 | 2025-07-09
MEP VFC IFC (Input for Construction) | 28 | 2025-04-02 | 2025-04-30 | 2025-05-28 | 2025-06-25 | 2025-07-23 | 2025-08-20
Structural VFC for first 5-10 floors above ground** | 32 | 2025-04-30 | 2025-05-28 | 2025-06-25 | 2025-07-23 | 2025-08-20 | 2025-09-17
- Facade Cast-in Details | 26 | 2025-03-19 | 2025-04-16 | 2025-05-14 | 2025-06-11 | 2025-07-09 | 2025-08-06
- Coordinated GA3for first 5-10 floors above ground | 26 | 2025-03-19 | 2025-04-16 | 2025-05-14 | 2025-06-11 | 2025-07-09 | 2025-08-06
- Structural VFC4 (Internal) | 28 | 2025-04-02 | 2025-04-30 | 2025-05-28 | 2025-06-25 | 2025-07-23 | 2025-08-20
- ID Concept Finalization7,8 | 28 | 2025-04-02 | 2025-04-30 | 2025-05-28 | 2025-06-25 | 2025-07-23 | 2025-08-20
- MEP IFC6 | 30 | 2025-04-16 | 2025-05-14 | 2025-06-11 | 2025-07-09 | 2025-08-06 | 2025-09-03
- Civil DD for Entire Building | 28 | 2025-04-02 | 2025-04-30 | 2025-05-28 | 2025-06-25 | 2025-07-23 | 2025-08-20
MEP VFC IFC (Input for Construction) | 36 | 2025-05-28 | 2025-06-25 | 2025-07-23 | 2025-08-20 | 2025-09-17 | 2025-10-15
Structural VFC for balance structure (100%)*** | 48 | 2025-08-20 | 2025-09-17 | 2025-10-15 | 2025-11-12 | 2025-12-10 | 2026-01-07
- Coordinated GA3 for balance structure (100%) | 40 | 2025-06-25 | 2025-07-23 | 2025-08-20 | 2025-09-17 | 2025-10-15 | 2025-11-12
- Structural VFC4 (Internal) | 42 | 2025-07-09 | 2025-08-06 | 2025-09-03 | 2025-10-01 | 2025-10-29 | 2025-11-26
- MEP IFC6 | 46 | 2025-08-06 | 2025-09-03 | 2025-10-01 | 2025-10-29 | 2025-11-26 | 2025-12-24
- Civil DD for balance Structure (100%) | 46 | 2025-08-06 | 2025-09-03 | 2025-10-01 | 2025-10-29 | 2025-11-26 | 2025-12-24
MEP VFC IFC (Input for Construction) | 52 | 2025-09-17 | 2025-10-15 | 2025-11-12 | 2025-12-10 | 2026-01-07 | 2026-02-04
Facade tender (including windows and external painting) | 44 | 2025-07-23 | 2025-08-20 | 2025-09-17 | 2025-10-15 | 2025-11-12 | 2025-12-10
Facade mockup / Testing (for high rise and super high rise only) | 74 | 2026-02-18 | 2026-03-18 | 2026-04-15 | 2026-05-13 | 2026-06-10 | 2026-07-08
MEP Tender | 71 | 2026-01-28 | 2026-02-25 | 2026-03-25 | 2026-04-22 | 2026-05-20 | 2026-06-17
Fitouts Tender | 71 | 2026-01-28 | 2026-02-25 | 2026-03-25 | 2026-04-22 | 2026-05-20 | 2026-06-17
Lifts Tender | 71 | 2026-01-28 | 2026-02-25 | 2026-03-25 | 2026-04-22 | 2026-05-20 | 2026-06-17
BMS & Security System Tender | 83 | 2026-04-22 | 2026-05-20 | 2026-06-17 | 2026-07-15 | 2026-08-12 | 2026-09-09
All other tenders related to the building | 83 | 2026-04-22 | 2026-05-20 | 2026-06-17 | 2026-07-15 | 2026-08-12 | 2026-09-09
MEP VFC | NA | NA | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Fitouts VFC | 67 | 2025-12-31 | 2026-01-28 | 2026-02-25 | 2026-03-25 | 2026-04-22 | 2026-05-20
MEP VFC for Fitouts | 69 | 2026-01-14 | 2026-02-11 | 2026-03-11 | 2026-04-08 | 2026-05-06 | 2026-06-03
VFC for all other tenders related to the building | 68 | 2026-01-07 | 2026-02-04 | 2026-03-04 | 2026-04-01 | 2026-04-29 | 2026-05-27
100% MEP Shop Drawings (part interim approvals shall be done) | 88 | 2026-05-27 | 2026-06-24 | 2026-07-22 | 2026-08-19 | 2026-09-16 | 2026-10-14
DESIGN COMPLETION | 88 | 2026-05-27 | 2026-06-24 | 2026-07-22 | 2026-08-19 | 2026-09-16 | 2026-10-14
Completion | 135 | 2027-04-21 | 2027-05-19 | 2027-06-16 | 2027-07-14 | 2027-08-11 | 2027-09-08
Formulas:
RESI = IFERROR((D7+(7*[Policy # of Weeks])),"NA")
RESI = [RESI]+28

## Details-MEP
|  |  |  | PHASE-1- Residential tower | [15 empty] | PHASE-2
|  |  |  | T1 |  | T2 |  | T3 |  | T4 |  | T5 |  | T6 |  | INFRA-1 |  | MLCP |  | T7 |  | T8 |  | T9 |  | INFRA-2 |  | KCA
Sr. No. | Deliverable | Trade | Duration as per Actual in Weeks | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | REMARKS
1 | Project Start Date (Email from AML sir) |  |  | 2024-06-26
2 | Concept Finalization |  | 12 | 2024-09-18 |  | 2024-10-16 |  | 2024-11-13 |  | 2024-12-11 |  | 2025-01-08 |  | 2025-02-05 | [5 empty] | 2024-06-26
A | Design Stage
1 | Concept | Architecture | 7 | 2024-08-14 |  | 2024-09-11 |  | 2024-10-09 |  | 2024-11-06 |  | 2024-12-04 |  | 2025-01-01 |  | 2024-08-14 |  | 2024-08-14
|  | Structure | 2 | 2024-08-28 |  | 2024-09-25 |  | 2024-10-23 |  | 2024-11-20 |  | 2024-12-18 |  | 2025-01-15 |  | 2024-08-28 |  | 2024-08-28
|  | MEP | 4 | 2024-09-11 |  | 2024-10-09 |  | 2024-11-06 |  | 2024-12-04 |  | 2025-01-01 |  | 2025-01-29 |  | 2024-09-11 |  | 2024-09-11
1 |  | Workshop | 5 | 2024-09-18 |  | 2024-10-16 |  | 2024-11-13 |  | 2024-12-11 |  | 2025-01-08 |  | 2025-02-05 |  | 2024-09-18 |  | 2024-09-18
1 | Schematic | Architecture | 3 | 2024-10-09 |  | 2024-11-06 |  | 2024-12-04 |  | 2025-01-01 |  | 2025-01-29 |  | 2025-02-26 |  | 2024-10-09 |  | 2024-10-09
|  | Structure | 2 | 2024-10-23 |  | 2024-11-20 |  | 2024-12-18 |  | 2025-01-15 |  | 2025-02-12 |  | 2025-03-12 |  | 2024-10-23 |  | 2024-10-23
|  | MEP | 3 | 2024-10-30 |  | 2024-11-27 |  | 2024-12-25 |  | 2025-01-22 |  | 2025-02-19 |  | 2025-03-19 |  | 2024-10-30 |  | 2024-10-30
1 |  | Workshop | 4 | 2024-11-06 |  | 2024-12-04 |  | 2025-01-01 |  | 2025-01-29 |  | 2025-02-26 |  | 2025-03-26 |  | 2024-11-06 |  | 2024-11-06
1 | DD | Architecture | 4 | 2024-12-04 |  | 2025-01-01 |  | 2025-01-29 |  | 2025-02-26 |  | 2025-03-26 |  | 2025-04-23 |  | 2024-12-04 |  | 2024-12-04
|  | Structure | 2 | 2024-12-18 |  | 2025-01-15 |  | 2025-02-12 |  | 2025-03-12 |  | 2025-04-09 |  | 2025-05-07 |  | 2024-12-18 |  | 2024-12-18
|  | MEP | 6 | 2025-01-15 |  | 2025-02-12 |  | 2025-03-12 |  | 2025-04-09 |  | 2025-05-07 |  | 2025-06-04 |  | 2025-01-15 |  | 2025-01-15
1 |  | Workshop | 7 | 2025-01-22 |  | 2025-02-19 |  | 2025-03-19 |  | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11 |  | 2025-01-22 |  | 2025-01-22
B | Tender
1 | Excavation Tender (Based on requirement) | Structure
2 | Civil Tender | Structure
3 | Piling Tender | Structure
4 | Piling VFC | Structure
5 | Earthing Tender (Micro Pile) | MEP | 4 | 2024-11-20 |  | 2024-12-18 |  | 2025-01-15 |  | 2025-02-12 |  | 2025-03-12 |  | 2025-04-09 |  | 2024-11-20 |  | 2024-11-20
6 | Electrical concealed tender | MEP | 6 | 2025-01-15 |  | 2025-02-12 |  | 2025-03-12 |  | 2025-04-09 |  | 2025-05-07 |  | 2025-06-04 |  | 2025-01-15 |  | 2025-01-15
7 | PHE | MEP | 7 | 2025-03-12 |  | 2025-04-09 |  | 2025-05-07 |  | 2025-06-04 |  | 2025-07-02 |  | 2025-07-02 |  | 2025-03-12 |  | 2025-03-12
8 | Fire Fighting | MEP | 6 | 2025-03-05 |  | 2025-04-02 |  | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25 |  | 2025-06-25 |  | 2025-03-05 |  | 2025-03-05
9 | FAVA | MEP | 9 | 2025-03-26 |  | 2025-04-23 |  | 2025-05-21 |  | 2025-06-18 |  | 2025-07-16 |  | 2025-07-16 |  | 2025-03-26 |  | 2025-03-26
10 | HVAC | MEP | 12 | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11 |  | 2025-07-09 |  | 2025-08-06 |  | 2025-08-06 |  | 2025-04-16 |  | 2025-04-16
11 | Security (CCTV, access control, intercom) | MEP | 13 | 2025-04-23 |  | 2025-05-21 |  | 2025-06-18 |  | 2025-07-16 |  | 2025-08-13 |  | 2025-08-13 |  | 2025-04-23 |  | 2025-04-23
12 | Electrical | MEP | 6 | 2025-03-05 |  | 2025-04-02 |  | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25 |  | 2025-06-25 |  | 2025-03-05 |  | 2025-03-05
13 | VDP | MEP | 12 | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11 |  | 2025-07-09 |  | 2025-08-06 |  | 2025-08-06 |  | 2025-04-16 |  | 2025-04-16
14 | IBS & FTTH RFP | MEP | 12 | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11 |  | 2025-07-09 |  | 2025-08-06 |  | 2025-08-06 |  | 2025-04-16 |  | 2025-04-16
15 | LIFTS | MEP | 14 | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25 |  | 2025-07-23 |  | 2025-08-20 |  | 2025-08-20 |  | 2025-04-30 |  | 2025-04-30
16 | Roof Top solar Hot water | MEP | 15 | 2025-05-07 |  | 2025-06-04 |  | 2025-07-02 |  | 2025-07-30 |  | 2025-08-27 |  | 2025-08-27 |  | 2025-05-07 |  | 2025-05-07
17 | Centralized Ventilation | MEP | 10 | 2025-04-02 |  | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25 |  | 2025-07-23 |  | 2025-07-23 |  | 2025-04-02 |  | 2025-04-02
18 | OWC | MEP | 14 | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25 |  | 2025-07-23 |  | 2025-08-20 |  | 2025-08-20 |  | 2025-04-30 |  | 2025-04-30
19 | STP | MEP | 14 | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25 |  | 2025-07-23 |  | 2025-08-20 |  | 2025-08-20 |  | 2025-04-30 |  | 2025-04-30
20 | WTP | MEP | 14 | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25 |  | 2025-07-23 |  | 2025-08-20 |  | 2025-08-20 |  | 2025-04-30 |  | 2025-04-30
21 | STP & OWC De-Odorization | MEP | 15 | 2025-05-07 |  | 2025-06-04 |  | 2025-07-02 |  | 2025-07-30 |  | 2025-08-27 |  | 2025-08-27 |  | 2025-05-07 |  | 2025-05-07
22 | DG | MEP | 16 | 2025-05-14 |  | 2025-06-11 |  | 2025-07-09 |  | 2025-08-06 |  | 2025-09-03 |  | 2025-09-03 |  | 2025-05-14 |  | 2025-05-14
23 | PNG | MEP | 17 | 2025-05-21 |  | 2025-06-18 |  | 2025-07-16 |  | 2025-08-13 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-05-21 |  | 2025-05-21
24 | RWH | MEP | 18 | 2025-05-28 |  | 2025-06-25 |  | 2025-07-23 |  | 2025-08-20 |  | 2025-09-17 |  | 2025-09-17 |  | 2025-05-28 |  | 2025-05-28
25 | Swimming Pool | MEP | 5 | 2025-02-26 |  | 2025-03-26 |  | 2025-03-19 |  | 2025-04-16 |  | 2025-05-14 |  | 2025-05-14 |  | 2025-02-26 |  | 2025-02-26
26 | Fitout | ID
C | VFC
1.1 | Aluminium formwork Shell Plan (Base drawings for preparing shell plan) | Architecture
1.2 |  | Structure
1.3 |  | MEP
2.1 | Podium 1 | Architecture
2.2 |  | Structure
2.3 |  | MEP
3.1 | Podium 2 | Architecture
3.2 |  | Structure
3.3 |  | MEP
4.1 | Podium 3 | Architecture
4.2 |  | Structure
4.3 |  | MEP
5.1 | Podium 4 | Architecture
5.2 |  | Structure
5.3 |  | MEP
6.1 | Podium 5 | Architecture
6.2 |  | Structure
6.3 |  | MEP
7.1 | Podium 6 | Architecture
7.2 |  | Structure
7.3 |  | MEP
8.1 | Podium TOP | Architecture
8.2 |  | Structure
8.3 |  | MEP
9.1 | Garden Unit | Architecture | 2 | 2025-02-05 |  | 2025-03-05 |  | 2025-04-02 |  | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25
9.2 |  | Structure | 1 | 2025-01-29 |  | 2025-02-26 |  | 2025-03-26 |  | 2025-04-23 |  | 2025-05-21 |  | 2025-06-18
9.3 |  | MEP | 2 | 2025-02-05 |  | 2025-03-05 |  | 2025-04-02 |  | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25
10.1 | Typical Floor | Architecture | 3 | 2025-02-12 |  | 2025-03-12 |  | 2025-04-09 |  | 2025-05-07 |  | 2025-06-04 |  | 2025-07-02
10.2 |  | Structure | 1 | 2025-01-29 |  | 2025-02-26 |  | 2025-03-26 |  | 2025-04-23 |  | 2025-05-21 |  | 2025-06-18
10.3 |  | MEP | 2 | 2025-02-05 |  | 2025-03-05 |  | 2025-04-02 |  | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25
11.1 | REFUGE | Architecture | 4 | 2025-02-19 |  | 2025-03-19 |  | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11 |  | 2025-07-09
11.2 |  | Structure | 1 | 2025-01-29 |  | 2025-02-26 |  | 2025-03-26 |  | 2025-04-23 |  | 2025-05-21 |  | 2025-06-18
11.3 |  | MEP | 2 | 2025-02-05 |  | 2025-03-05 |  | 2025-04-02 |  | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25
12.1 | Penthouse level | Architecture | 5 | 2025-02-26 |  | 2025-03-26 |  | 2025-04-23 |  | 2025-05-21 |  | 2025-06-18 |  | 2025-07-16
12.2 |  | Structure | 1 | 2025-01-29 |  | 2025-02-26 |  | 2025-03-26 |  | 2025-04-23 |  | 2025-05-21 |  | 2025-06-18
12.3 |  | MEP | 2 | 2025-02-05 |  | 2025-03-05 |  | 2025-04-02 |  | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25
13.1 | Terrace | Architecture | 6 | 2025-03-05 |  | 2025-04-02 |  | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25 |  | 2025-07-23
13.2 |  | Structure | 1 | 2025-01-29 |  | 2025-02-26 |  | 2025-03-26 |  | 2025-04-23 |  | 2025-05-21 |  | 2025-06-18
13.3 |  | MEP | 2 | 2025-02-05 |  | 2025-03-05 |  | 2025-04-02 |  | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25
14.1 | OHT Top | Architecture | 7 | 2025-03-12 |  | 2025-04-09 |  | 2025-05-07 |  | 2025-04-16 |  | 2025-07-02 |  | 2025-07-30
14.2 |  | Structure | 1 | 2025-03-19 |  | 2025-04-16 |  | 2025-05-07 |  | 2025-04-23 |  | 2025-07-09 |  | 2025-08-06
14.3 |  | MEP | 2 | 2025-03-26 |  | 2025-04-23 |  | 2025-05-21 |  | 2025-04-30 |  | 2025-07-23 |  | 2025-08-20
15 | Schematic (If SLD, then required with Tender) | MEP | 12 | 2025-04-30 |  | 2025-05-14 |  | 2025-06-11 |  | 2025-07-09 |  | 2025-08-06 |  | 2025-09-03
Formulas:
T1 = IFERROR((E4+(7*[Duration as per Actual in Weeks])),"NA")
T1 = +E4+([Duration as per Actual in Weeks]*7)
T2 = +[T1]+(4*7)
T2 = +[T2, row above]+([Duration as per Actual in Weeks]*7)
T3 = +[T2]+(4*7)
T3 = +[T3, row above]+([Duration as per Actual in Weeks]*7)
T4 = +[T3]+(4*7)
T4 = +[T4, row above]+([Duration as per Actual in Weeks]*7)
T5 = +[T4]+(4*7)
T5 = +[T5, row above]+([Duration as per Actual in Weeks]*7)
T6 = +[T5]+(4*7)
T6 = +[T6, row above]+([Duration as per Actual in Weeks]*7)
T7 = IFERROR((E4+(7*[Actual])),"NA")
INFRA-1 = +[T1]
MLCP = +[T1]

## Draft Dates for LEAD
|  |  |  | PHASE-1- Residential tower | [15 empty] | PHASE-2
|  |  |  | T1 |  | T2 |  | T3 |  | T4 |  | T5 |  | T6 |  | INFRA-1 |  | MLCP |  | T7 |  | T8 |  | T9 |  | INFRA-2 |  | KCA
Sr. No. | Deliverable | Trade | Duration as per Actual in Weeks | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | REMARKS
1 | Project Start Date (Email from AML sir) |  |  | 2024-06-26
2 | Concept Finalization |  | 10 | 2024-09-04 |  | 2024-10-02 |  | 2024-10-30 |  | 2024-11-27 |  | 2024-12-25 |  | 2025-01-22 | [5 empty] | 2024-06-26
A | Design Stage
1 | Concept | Architecture | 5 | 2024-07-31 |  | 2024-08-28 |  | 2024-09-25 |  | 2024-10-23 |  | 2024-11-20 |  | 2024-12-18 |  | 2024-07-31 |  | 2024-07-31
|  | Structure | 2 | 2024-08-14 |  | 2024-09-11 |  | 2024-10-09 |  | 2024-11-06 |  | 2024-12-04 |  | 2025-01-01 |  | 2024-08-14 |  | 2024-08-14
|  | MEP | 4 | 2024-08-28 |  | 2024-09-25 |  | 2024-10-23 |  | 2024-11-20 |  | 2024-12-18 |  | 2025-01-15 |  | 2024-08-28 |  | 2024-08-28
|  | Workshop | 5 | 2024-09-04 |  | 2024-10-02 |  | 2024-10-30 |  | 2024-11-27 |  | 2024-12-25 |  | 2025-01-22 |  | 2024-09-04 |  | 2024-09-04
2 | Schematic | Architecture | 3 | 2024-09-25 |  | 2024-10-23 |  | 2024-11-20 |  | 2024-12-18 |  | 2025-01-15 |  | 2025-02-12 |  | 2024-09-25 |  | 2024-09-25
|  | Structure | 2 | 2024-10-09 |  | 2024-11-06 |  | 2024-12-04 |  | 2025-01-01 |  | 2025-01-29 |  | 2025-02-26 |  | 2024-10-09 |  | 2024-10-09
|  | MEP | 3 | 2024-10-16 |  | 2024-11-13 |  | 2024-12-11 |  | 2025-01-08 |  | 2025-02-05 |  | 2025-03-05 |  | 2024-10-16 |  | 2024-10-16
|  | Workshop | 4 | 2024-10-23 |  | 2024-11-20 |  | 2024-12-18 |  | 2025-01-15 |  | 2025-02-12 |  | 2025-03-12 |  | 2024-10-23 |  | 2024-10-23
3 | DD | Architecture | 4 | 2024-11-20 |  | 2024-12-18 |  | 2025-01-15 |  | 2025-02-12 |  | 2025-03-12 |  | 2025-04-09 |  | 2024-11-20 |  | 2024-11-20
|  | Structure | 2 | 2024-12-04 |  | 2025-01-01 |  | 2025-01-29 |  | 2025-02-26 |  | 2025-03-26 |  | 2025-04-23 |  | 2024-12-04 |  | 2024-12-04
|  | MEP | 6 | 2025-01-01 |  | 2025-01-29 |  | 2025-02-26 |  | 2025-03-26 |  | 2025-04-23 |  | 2025-05-21 |  | 2025-01-01 |  | 2025-01-01
|  | Workshop | 7 | 2025-01-08 |  | 2025-02-05 |  | 2025-03-05 |  | 2025-04-02 |  | 2025-04-30 |  | 2025-05-28 |  | 2025-01-08 |  | 2025-01-08
B | Tender
1 | Earthing Tender (Micro Pile) | MEP | 4 | 2024-11-06 |  | 2024-12-04 |  | 2025-01-01 |  | 2025-01-29 |  | 2025-02-26 |  | 2025-03-26 |  | 2024-11-06 |  | 2024-11-06
2 | Electrical concealed tender | MEP | 6 | 2025-01-01 |  | 2025-01-29 |  | 2025-02-26 |  | 2025-03-26 |  | 2025-04-23 |  | 2025-05-21 |  | 2025-01-01 |  | 2025-01-01
3 | PHE | MEP | 7 | 2025-02-26 |  | 2025-03-26 |  | 2025-04-23 |  | 2025-05-21 |  | 2025-06-18 |  | 2025-06-18 |  | 2025-02-26 |  | 2025-02-26
4 | Fire Fighting | MEP | 6 | 2025-02-19 |  | 2025-03-19 |  | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11 |  | 2025-06-11 |  | 2025-02-19 |  | 2025-02-19
5 | FAVA | MEP | 9 | 2025-03-12 |  | 2025-04-09 |  | 2025-05-07 |  | 2025-06-04 |  | 2025-07-02 |  | 2025-07-02 |  | 2025-03-12 |  | 2025-03-12
6 | HVAC | MEP | 12 | 2025-04-02 |  | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25 |  | 2025-07-23 |  | 2025-07-23 |  | 2025-04-02 |  | 2025-04-02
7 | Security (CCTV, access control, intercom) | MEP | 13 | 2025-04-09 |  | 2025-05-07 |  | 2025-06-04 |  | 2025-07-02 |  | 2025-07-30 |  | 2025-07-30 |  | 2025-04-09 |  | 2025-04-09
8 | Electrical | MEP | 6 | 2025-02-19 |  | 2025-03-19 |  | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11 |  | 2025-06-11 |  | 2025-02-19 |  | 2025-02-19
9 | VDP | MEP | 12 | 2025-04-02 |  | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25 |  | 2025-07-23 |  | 2025-07-23 |  | 2025-04-02 |  | 2025-04-02
10 | IBS & FTTH RFP | MEP | 12 | 2025-04-02 |  | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25 |  | 2025-07-23 |  | 2025-07-23 |  | 2025-04-02 |  | 2025-04-02
11 | LIFTS | MEP | 14 | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11 |  | 2025-07-09 |  | 2025-08-06 |  | 2025-08-06 |  | 2025-04-16 |  | 2025-04-16
12 | Roof Top solar Hot water | MEP | 15 | 2025-04-23 |  | 2025-05-21 |  | 2025-06-18 |  | 2025-07-16 |  | 2025-08-13 |  | 2025-08-13 |  | 2025-04-23 |  | 2025-04-23
13 | Centralized Ventilation | MEP | 10 | 2025-03-19 |  | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11 |  | 2025-07-09 |  | 2025-07-09 |  | 2025-03-19 |  | 2025-03-19
14 | OWC | MEP | 14 | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11 |  | 2025-07-09 |  | 2025-08-06 |  | 2025-08-06 |  | 2025-04-16 |  | 2025-04-16
15 | STP | MEP | 14 | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11 |  | 2025-07-09 |  | 2025-08-06 |  | 2025-08-06 |  | 2025-04-16 |  | 2025-04-16
16 | WTP | MEP | 14 | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11 |  | 2025-07-09 |  | 2025-08-06 |  | 2025-08-06 |  | 2025-04-16 |  | 2025-04-16
17 | STP & OWC De-Odorization | MEP | 15 | 2025-04-23 |  | 2025-05-21 |  | 2025-06-18 |  | 2025-07-16 |  | 2025-08-13 |  | 2025-08-13 |  | 2025-04-23 |  | 2025-04-23
18 | DG | MEP | 16 | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25 |  | 2025-07-23 |  | 2025-08-20 |  | 2025-08-20 |  | 2025-04-30 |  | 2025-04-30
19 | PNG | MEP | 17 | 2025-05-07 |  | 2025-06-04 |  | 2025-07-02 |  | 2025-07-30 |  | 2025-08-27 |  | 2025-08-27 |  | 2025-05-07 |  | 2025-05-07
20 | RWH | MEP | 18 | 2025-05-14 |  | 2025-06-11 |  | 2025-07-09 |  | 2025-08-06 |  | 2025-09-03 |  | 2025-09-03 |  | 2025-05-14 |  | 2025-05-14
21 | Swimming Pool | MEP | 5 | 2025-02-12 |  | 2025-03-12 |  | 2025-03-05 |  | 2025-04-02 |  | 2025-04-30 |  | 2025-04-30 |  | 2025-02-12 |  | 2025-02-12
22 | Fitout | ID
C | VFC
1.1 | Aluminium formwork Shell Plan (Base drawings for preparing shell plan) | Architecture
1.2 |  | Structure
1.3 |  | MEP
2.1 | Podium 1 | Architecture
2.2 |  | Structure
2.3 |  | MEP
3.1 | Podium 2 | Architecture
3.2 |  | Structure
3.3 |  | MEP
4.1 | Podium 3 | Architecture
4.2 |  | Structure
4.3 |  | MEP
5.1 | Podium 4 | Architecture
5.2 |  | Structure
5.3 |  | MEP
6.1 | Podium 5 | Architecture
6.2 |  | Structure
6.3 |  | MEP
7.1 | Podium 6 | Architecture
7.2 |  | Structure
7.3 |  | MEP
8.1 | Podium TOP | Architecture
8.2 |  | Structure
8.3 |  | MEP
9.1 | Garden Unit | Architecture | 2 | 2025-01-22 |  | 2025-02-19 |  | 2025-03-19 |  | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11
9.2 |  | Structure | 1 | 2025-01-15 |  | 2025-02-12 |  | 2025-03-12 |  | 2025-04-09 |  | 2025-05-07 |  | 2025-06-04
9.3 |  | MEP | 2 | 2025-01-22 |  | 2025-02-19 |  | 2025-03-19 |  | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11
10.1 | Typical Floor | Architecture | 3 | 2025-01-29 |  | 2025-02-26 |  | 2025-03-26 |  | 2025-04-23 |  | 2025-05-21 |  | 2025-06-18
10.2 |  | Structure | 1 | 2025-01-15 |  | 2025-02-12 |  | 2025-03-12 |  | 2025-04-09 |  | 2025-05-07 |  | 2025-06-04
10.3 |  | MEP | 2 | 2025-01-22 |  | 2025-02-19 |  | 2025-03-19 |  | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11
11.1 | REFUGE | Architecture | 4 | 2025-02-05 |  | 2025-03-05 |  | 2025-04-02 |  | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25
11.2 |  | Structure | 1 | 2025-01-15 |  | 2025-02-12 |  | 2025-03-12 |  | 2025-04-09 |  | 2025-05-07 |  | 2025-06-04
11.3 |  | MEP | 2 | 2025-01-22 |  | 2025-02-19 |  | 2025-03-19 |  | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11
12.1 | Penthouse level | Architecture | 5 | 2025-02-12 |  | 2025-03-12 |  | 2025-04-09 |  | 2025-05-07 |  | 2025-06-04 |  | 2025-07-02
12.2 |  | Structure | 1 | 2025-01-15 |  | 2025-02-12 |  | 2025-03-12 |  | 2025-04-09 |  | 2025-05-07 |  | 2025-06-04
12.3 |  | MEP | 2 | 2025-01-22 |  | 2025-02-19 |  | 2025-03-19 |  | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11
13.1 | Terrace | Architecture | 6 | 2025-02-19 |  | 2025-03-19 |  | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11 |  | 2025-07-09
13.2 |  | Structure | 1 | 2025-01-15 |  | 2025-02-12 |  | 2025-03-12 |  | 2025-04-09 |  | 2025-05-07 |  | 2025-06-04
13.3 |  | MEP | 2 | 2025-01-22 |  | 2025-02-19 |  | 2025-03-19 |  | 2025-04-16 |  | 2025-05-14 |  | 2025-06-11
14.1 | OHT Top | Architecture | 7 | 2025-02-26 |  | 2025-03-26 |  | 2025-04-23 |  | 2025-04-02 |  | 2025-06-18 |  | 2025-07-16
14.2 |  | Structure | 1 | 2025-03-05 |  | 2025-04-02 |  | 2025-04-23 |  | 2025-04-09 |  | 2025-06-25 |  | 2025-07-23
14.3 |  | MEP | 2 | 2025-03-12 |  | 2025-04-09 |  | 2025-05-07 |  | 2025-04-16 |  | 2025-07-09 |  | 2025-08-06
15 | Schematic (If SLD, then required with Tender) | MEP | 12 | 2025-04-16 |  | 2025-04-30 |  | 2025-05-28 |  | 2025-06-25 |  | 2025-07-23 |  | 2025-08-20
Formulas:
T1 = IFERROR((E4+(7*[Duration as per Actual in Weeks])),"NA")
T1 = +E4+([Duration as per Actual in Weeks]*7)
T2 = +[T1]+(4*7)
T2 = +[T2, row above]+([Duration as per Actual in Weeks]*7)
T3 = +[T2]+(4*7)
T3 = +[T3, row above]+([Duration as per Actual in Weeks]*7)
T4 = +[T3]+(4*7)
T4 = +[T4, row above]+([Duration as per Actual in Weeks]*7)
T5 = +[T4]+(4*7)
T5 = +[T5, row above]+([Duration as per Actual in Weeks]*7)
T6 = +[T5]+(4*7)
T6 = +[T6, row above]+([Duration as per Actual in Weeks]*7)
T7 = IFERROR((E4+(7*[Actual])),"NA")
INFRA-1 = +[T1]
MLCP = +[T1]

## VFC Drawing List
Sr. No. | Trade | Doc Type | Tower | Level | Description | Document/ Drawing Number | Rev. No. | Paper size | Drawing Scale | SNC DDS date | STATUS | REMARKS
VFC Layouts
1 | Fire Fighting | Drawing | Tower-1 | STILT/GROUND FLOOR | Fire Fighting Layout for Stilt floor/Ground floor
2 | Fire Fighting | Drawing | Tower-1 | TYPICAL FLOOR | Fire Fighting Layout for Typical floor
3 | Fire Fighting | Drawing | Tower-1 | TYPICAL REFUGE FLOOR | Fire Fighting Layout for Typical refuge
4 | Fire Fighting | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for Roof level
5 | Fire Fighting | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for LMR level
6 | Fire Fighting | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for Terrace level
7 | PHE | Drawing | Tower-1 | PLINTH LEVE | Plumbing Layout for plinth level
8 | PHE | Drawing | Tower-1 | STILT/GROUND FLOOR | Plumbing ceiling Layout for Stilt floor/Ground floor
9 | PHE | Drawing | Tower-1 | TYPICAL FLOOR | Plumbing Layout for Typical floor
10 | PHE | Drawing | Tower-1 | TYPICAL REFUGE FLOOR | Plumbing Layout for Typical refuge
11 | PHE | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for Roof level
12 | PHE | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for LMR level
13 | PHE | Drawing | Tower-1 | TERRACE FLOOR | Plumbing Layout for Terrace level
14 | HVAC | Drawing | Tower-1 | STILT/GROUND FLOOR | HVAC Layout for Stilt floor/Ground floor
15 | HVAC | Drawing | Tower-1 | TYPICAL FLOOR | HVAC Layout for Typical floor
16 | HVAC | Drawing | Tower-1 | TYPICAL REFUGE FLOOR | HVAC Layout for Typical refuge
17 | HVAC | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for Roof level
18 | HVAC | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for LMR level
19 | HVAC | Drawing | Tower-1 | TERRACE FLOOR | HVAC Layout for Terrace level
20 | Lighting | Drawing | Tower-1 | STILT/GROUND FLOOR | Lighting Layout for Stilt floor/Ground floor
21 | Lighting | Drawing | Tower-1 | TYPICAL FLOOR | Lighting Layout for Typical floor
22 | Lighting | Drawing | Tower-1 | TYPICAL REFUGE FLOOR | Lighting Layout for Typical refuge
23 | Lighting | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for Roof level
24 | Lighting | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for LMR level
25 | Lighting | Drawing | Tower-1 | TERRACE FLOOR | Lighting Layout for Terrace level
26 | Small Power | Drawing | Tower-1 | STILT/GROUND FLOOR | Small power Layout for Stilt floor/Ground floor
27 | Small Power | Drawing | Tower-1 | TYPICAL FLOOR | Small power Layout for Typical floor
28 | Small Power | Drawing | Tower-1 | TYPICAL REFUGE FLOOR | Small power Layout for Typical refuge
29 | Small Power | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for Roof level
30 | Small Power | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for LMR level
31 | Small Power | Drawing | Tower-1 | TERRACE FLOOR | Small power Layout for Terrace level
32 | Lightning Protection | Drawing | Tower-1 | STILT/GROUND FLOOR | Lightning protection Layout for Stilt floor/Ground floor
33 | Lightning Protection | Drawing | Tower-1 | STILT/GROUND FLOOR | Lightning protection Layout for Typical floor
34 | Lightning Protection | Drawing | Tower-1 | TYPICAL REFUGE FLOOR | Lightning protection Layout for Typical refuge
35 | Lightning Protection | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for Roof level
36 | Lightning Protection | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for LMR level
37 | Lightning Protection | Drawing | Tower-1 | TERRACE FLOOR | Lightning protection Layout for Terrace level
38 | Containment | Drawing | Tower-1 | STILT/GROUND FLOOR | Containment Layout for Stilt floor/Ground floor
39 | Containment | Drawing | Tower-1 | TYPICAL FLOOR | Containment Layout for Typical floor
40 | Containment | Drawing | Tower-1 | TYPICAL REFUGE FLOOR | Containment Layout for Typical refuge
41 | Containment | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for Roof level
42 | Containment | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for LMR level
43 | Containment | Drawing | Tower-1 | TERRACE FLOOR | Containment Layout for Terrace level
44 | FA & PA | Drawing | Tower-1 | STILT/GROUND FLOOR | FAPA Layout for Stilt floor/Ground floor
45 | FA & PA | Drawing | Tower-1 | TYPICAL FLOOR | FAPA Layout for Typical floor
46 | FA & PA | Drawing | Tower-1 | TYPICAL REFUGE FLOOR | FAPA Layout for Typical refuge
47 | FA & PA | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for Roof level
48 | FA & PA | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for LMR level
49 | FA & PA | Drawing | Tower-1 | TERRACE FLOOR | FAPA Layout for Terrace level
50 | ELV | Drawing | Tower-1 | STILT/GROUND FLOOR | ELV Layout for Stilt floor/Ground floor
51 | ELV | Drawing | Tower-1 | TYPICAL FLOOR | ELV Layout for Typical floor
52 | ELV | Drawing | Tower-1 | TYPICAL REFUGE FLOOR | ELV Layout for Typical refuge
53 | ELV | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for Roof level
54 | ELV | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for LMR level
55 | ELV | Drawing | Tower-1 | TERRACE FLOOR | ELV Layout for Terrace level

## DD Drawing List
List of MEP DD deliverables for Bhandup Project
Sr. No. | Trade | Doc Type | Tower | Level | Description | Document/ Drawing Number | Rev. No. | Paper size | Drawing Scale | LEAD DDS date | STATUS | REMARKS
A. Schematic - Calculations, document/note.
1 | Fire Fighting | Calculation | Tower-1 | As per CFO | UGT AND OHT TANK CAPACITY
2 |  | Calculation | Tower-1 |  | PUMP SIZING (FLOW RATE AND HEADER)
3 |  | Calculation | Tower-1 |  | PUMP HEADER
4 | Plumbing | Calculation | Tower-1 |  | UGT AND OHT TANK CAPACITY
5 |  | Calculation | Tower-1 |  | SUCTION HEADER SIZING
6 |  | Calculation | Tower-1 |  | PUMP CAPACITY OF TRANSFER, BOOSTER AND SUMP(FLOW RATE AND HEADER)
7 |  | Calculation | Tower-1 |  | TRANSFER PIPE SIZING
8 |  | Calculation | Tower-1 |  | TERRACE RAIN WATER PIPE SIZE
9 |  | Calculation | Tower-1 |  | RAIN WATER CALCULATION(NUMBER OF PIPE AND PIPE DIAMETER)
10 | HVAC | Calculation | Tower-1 |  | HEAT LOAD (HAP AND EXCEL SUMMERY)
11 |  | Calculation | Tower-1 | Not applicable | BASEMENT & PUMP ROOM VENTIALTION NORMAL AND SMOKE EXHAUST CALCULATION
11 |  | Calculation | Tower-1 |  | LIFT WELL PRESSURIZATION
12 |  | Calculation | Tower-1 | Not applicable | CAR PARKING VENTILATION CALCULATION
13 | Electrical | Calculation | Tower-1 |  | LOAD CALCULATION WITH POWER BACK UP (NORMAL & EMERGENCY) CALCUL.
14 |  | Calculation | Tower-1 |  | CABLE SCHEDULE AND VOLTAGE DROP CALCULATION
15 |  | Calculation | Tower-1 |  | EARTHING STRIP SIZING
16 |  | Calculation | Tower-1 |  | LIGHTNING PROTECTION
17 |  | Calculation | Tower-1 |  | SHORT CIRCUIT CALCULATION
18 |  | Calculation | Tower-1 |  | RISK ANALYSIS CALCULATION
B. Schematics
19 | PHE | Schematic | Tower-1 |  | Water Supply Schematic
20 |  | Schematic | Tower-1 |  | Drainage Schematic
21 |  | Schematic | Tower-1 |  | Rain water schematic
22 | Fire Fighting | Schematic | Tower-1 |  | Fire Fighting Schematic
23 | HVAC | Schematic | Tower-1 |  | Condensate drain
24 |  | Schematic | Tower-1 |  | HAVC Schematic (Staircase, Lift Lobby & Lift well pressurisation)
25 | Electrical | Schematic | Tower-1 |  | Electrical SLD
26 | Earthing | Schematic | Tower-1 |  | Earthing Schematic
27 | Lightning Protection | Schematic | Tower-1 |  | Lightning protection schematic
28 | ELV | Schematic | Tower-1 | Not in scope | ELV schematic
29 | FAVA | Schematic | Tower-1 |  | FAVA schematic
CO Layouts
30 | Co-ordinate | Drawing | Tower-1 | PLINTH LVL | Co-ordinate Layout for Plinth lvl
31 | Co-ordinate | Drawing | Tower-1 | STILT/GROUND FLOOR | Co-ordinate Layout for Stilt/Ground floor
32 | Co-ordinate | Drawing | Tower-1 | TYPICAL FLOOR | Co-ordinate Layout for Typical floor
33 | Co-ordinate | Drawing | Tower-1 | REFUGE -8th, 15th & 22nd & 29th FLOOR | Co-ordinate Layout for refuge Level 8th, 15th & 22nd & 29th
34 | Co-ordinate | Drawing | Tower-1 | TERRACE FLOOR | Co-ordinate Layout for Terrace level
BW Layouts
35 | Builders work | Drawing | Tower-1 | PLINTH LVL | Builders work Layout for Plinth lvl
36 | Builders work | Drawing | Tower-1 | STILT/GROUND FLOOR | Builders work Layout for Stilt/Ground floor
37 | Builders work | Drawing | Tower-1 | TYPICAL FLOOR | Builders work Layout for Typical floor
38 | Builders work | Drawing | Tower-1 | REFUGE -8th, 15th & 22nd & 29th FLOOR | Builders work Layout for refuge Level 8th, 15th & 22nd & 29th
39 | Builders work | Drawing | Tower-1 | TERRACE FLOOR | Builders work Layout for Terrace level
HVAC Layouts
40 | HVAC | Drawing | Tower-1 | STILT/GROUND FLOOR | HVAC Layout for Stilt/Ground floor
41 | HVAC | Drawing | Tower-1 | TYPICAL FLOOR | HVAC Layout for Typical floor
42 | HVAC | Drawing | Tower-1 | REFUGE -8th, 15th & 22nd & 29th FLOOR | HVAC Layout for refuge Level 8th, 15th & 22nd & 29th
43 | HVAC | Drawing | Tower-1 | TERRACE FLOOR | HVAC Layout for Terrace level
FF Layouts
44 | Fire Fighting | Drawing | Tower-1 | STILT/GROUND FLOOR | Fire Fighting Layout for Stilt/Ground floor
45 | Fire Fighting | Drawing | Tower-1 | TYPICAL FLOOR | Fire Fighting Layout for Typical floor
46 | Fire Fighting | Drawing | Tower-1 | REFUGE -8th, 15th & 22nd & 29th FLOOR | Fire Fighting Layout for refuge Level 8th, 15th & 22nd & 29th
47 | Fire Fighting | Drawing | Tower-1 | TERRACE FLOOR | Fire Fighting Layout for Terrace level
48 | Fire Fighting | Drawing | Tower-1 | ABOVE TERRACE FLOOR | Fire Fighting Layout for Above Terrace level
PHE Layouts
49 | PHE | Drawing | Tower-1 | PLINTH LVL | Plumbing Layout for Plinth lvl
50 | PHE | Drawing | Tower-1 | STILT/GROUND FLOOR | Plumbing Layout for Stilt/Ground floor
51 | PHE | Drawing | Tower-1 | FIRST & SECOND FLOOR | Plumbing Layout for First & Second floor
52 | PHE | Drawing | Tower-1 | TYPICAL FLOOR | Plumbing Layout for Typical floor
53 | PHE | Drawing | Tower-1 | REFUGE -8th, 15th & 22nd & 29th FLOOR | Plumbing Layout for refuge Level 8th, 15th & 22nd & 29th
54 | PHE | Drawing | Tower-1 | TERRACE FLOOR | Plumbing Layout for Terrace level
55 | PHE | Drawing | Tower-1 | ABOVE TERRACE FLOOR | Plumbing Layout for Above Terrace level
CONTAINMENT Layouts
56 | Containment | Drawing | Tower-1 | STILT/GROUND FLOOR | Containment Layout for Stilt/Ground floor
57 | Containment | Drawing | Tower-1 | TYPICAL FLOOR | Containment Layout for Typical floor
58 | Containment | Drawing | Tower-1 | REFUGE -8th, 15th & 22nd & 29th FLOOR | Containment Layout for refuge Level 8th, 15th & 22nd & 29th
59 | Containment | Drawing | Tower-1 | TERRACE FLOOR | Containment Layout for Terrace level
LIGHTING Layouts
60 | Lighting | Drawing | Tower-1 | STILT/GROUND FLOOR | Lighting Layout for Stilt/Ground floor
61 | Lighting | Drawing | Tower-1 | TYPICAL FLOOR | Lighting Layout for Typical floor
62 | Lighting | Drawing | Tower-1 | REFUGE -8th, 15th & 22nd & 29th FLOOR | Lighting Layout for refuge Level 8th, 15th & 22nd & 29th
63 | Lighting | Drawing | Tower-1 | TERRACE FLOOR | Lighting Layout for Terrace level
SMALL POWER Layouts
64 | Small Power | Drawing | Tower-1 | STILT/GROUND FLOOR | Small Power Layout for Stilt/Ground floor
65 | Small Power | Drawing | Tower-1 | TYPICAL FLOOR | Small Power Layout for Typical floor
66 | Small Power | Drawing | Tower-1 | REFUGE -8th, 15th & 22nd & 29th FLOOR | Small Power Layout for refuge Level 8th, 15th & 22nd & 29th
67 | Small Power | Drawing | Tower-1 | TERRACE FLOOR | Small Power Layout for Terrace level
FAVA Layouts
68 | FAVA | Drawing | Tower-1 | STILT/GROUND FLOOR | FAVA Layout for Stilt/Ground floor
69 | FAVA | Drawing | Tower-1 | TYPICAL FLOOR | FAVA Layout for Typical floor
70 | FAVA | Drawing | Tower-1 | REFUGE -8th, 15th & 22nd & 29th FLOOR | FAVA Layout for refuge Level 8th, 15th & 22nd & 29th
71 | FAVA | Drawing | Tower-1 | TERRACE FLOOR | FAVA Layout for Terrace level
ELV Layouts
72 | ELV | Drawing | Tower-1 | STILT/GROUND FLOOR | ELV Layout for Stilt/Ground floor
73 | ELV | Drawing | Tower-1 | TYPICAL FLOOR | ELV Layout for Typical floor
74 | ELV | Drawing | Tower-1 | REFUGE -8th, 15th & 22nd & 29th FLOOR | ELV Layout for refuge Level 8th, 15th & 22nd & 29th
75 | ELV | Drawing | Tower-1 | TERRACE FLOOR | ELV Layout for Terrace level
LPS Layouts
76 | LPS | Drawing | Tower-1 | PLINTH LVL | Lightning Protection Layout for Plinth lvl
77 | LPS | Drawing | Tower-1 | STILT/GROUND FLOOR | Lightning Protection Layout for Stilt/Ground floor
78 | LPS | Drawing | Tower-1 | TYPICAL FLOOR | Lightning Protection Layout for Typical floor
79 | LPS | Drawing | Tower-1 | REFUGE -8th, 15th & 22nd & 29th FLOOR | Lightning Protection Layout for refuge Level 8th, 15th & 22nd & 29th
80 | LPS | Drawing | Tower-1 | TERRACE FLOOR | Lightning Protection Layout for Terrace level
81 | LPS | Drawing | Tower-1 | ABOVE TERRACE FLOOR | Lightning Protection Layout for above Terrace level
LPS Layouts
82 | Sketch | Drawing | Tower-1 | Dwg Refernce No. | Sketch for …. lvl
83 | Sketch | Drawing | Tower-1 | Dwg Refernce No. | Sketch for …. lvl
84 | Sketch | Drawing | Tower-1 | Dwg Refernce No. | Sketch for …. lvl
85 | Sketch | Drawing | Tower-1 | Dwg Refernce No. | Sketch for …. lvl
86 | Sketch | Drawing | Tower-1 | Dwg Refernce No. | Sketch for …. lvl