## Deliverables
S. No. | Column 4 | Deliverables | Remarks | Column 1 | Dependency | Dependent Stakeholders
1 | Concept | Design Brief | By our team; include all references to key policies | Project | Area Matrix, Project design brief | Architect
2 | Concept | DBR | include all basic calculations, concept sketches | Project | Society bifurcation | Strategy
3 | Concept | Space Planning Package | Including typical floor and Infra services | Project | Architecture plan, road section drawing | Architect
5 | Liaison | Utility Approval package | FF drawings, Water Calculation + Nos. of Meters, Electrical Load, Sewage drawing, Storm water network. | Project | Site Survey layout with identification of tie in points.
4 | Liaison | MoEF Package | As per MoEF checklist and calculation formats | Project | Space Matrix, NOCs, (CFO, SWD, Water Supply, Electrical, Sewer), Liaison Plan | Liason
6 | SLDs | PHE Schematics |  | Plant | Section and Elevation plan | Architect
7 | SLDs | Electrical Schematics |  | Plant | Section and Elevation plan | Architect
8 | SLDs | ELV Schematics | CCTV, Access control, Network Schematic, Boom Barrier, BMS. | Plant | Section and Elevation plan | Architect
9 | SLDs | Fire Fighting Schematics |  | Plant | Section and Elevation plan | Architect
10 | SLDs | FAVA Schematics |  | Plant | Section and Elevation plan | Architect
11 | SD | SD Package | incl. coordination for AC, sprinklers, structural interfaces, space planning closure for non-typical levels. Fit for shell drawing production. | Plant | Section and Elevation plan | All stakeholders
12 | DD | DD Package | Including equipment selection, | Plant | 1. Architectural + Structural coordinated R0 1 week after SD closure. 2. ID package R0 3 weeks after SD closure. 3.DD Package will be given 6 weeks after SD package | All stakeholders
13 | DD | DD - Plinth Level | incl Builder's Work | Plant | Sturcture plinth layout, and arch ground level | All stakeholders
14 | Detailed Calculations | Calc - Pumps and plant room | detailed calcs, incl. pumps of all categories | Plant
15 | Detailed Calculations | Calc - Pipe sizing | Include both pressurised and gravity systems | Plant
16 | Detailed Calculations | Calc - Heat load |  | Plant
17 | Detailed Calculations | Calc - Mechanical Ventilation | Include all cases, STP ventilation can be added later | Plant
18 | Detailed Calculations | Calc - Voltage drop, SC, Cable Schedule |  | Plant
19 | Detailed Calculations | Calc - Earthing |  | Plant
20 | Detailed Calculations | Calc - Lightning Protection System | Include risk analysis, solution definition and strip sizing | Plant
21 | BW | BW - Basement Levels | incl DD drawings | Plant | Changes from other stakeholders(Structure +Architecture) | Arch +Structure
22 | BW | BW - Podium Levels | incl DD drawings | Plant | VFC layout from Structure and architect
23 | BW | BW - P0 or Ground | incl DD drawings | Plant | VFC layout from Structure and architect
24 | BW | BW - Typical Levels | incl DD drawings | Plant | VFC layout from Structure and architect
25 | BW | BW - Refuge Levels | incl DD drawings | Plant | VFC layout from Structure and architect
26 | BW | BW - Service Level(s) | incl DD drawings | Plant | VFC layout from Structure and architect
27 | BW | BW - Penthouse floors | incl DD drawings | Plant | VFC layout from Structure and architect
28 | BW | BW - Terrace | incl DD drawings | Plant | VFC layout from Structure and architect
29 | Tender | Lift Tender |  | Project
30 | Tender | Electrical Tender | conduiting and lightning protection package not to be given | Plant
31 | Tender | PHE Tender | including solar hot water | Plant
32 | Tender | Fire Fighting Tender |  | Plant
33 | Tender | HVAC Tender |  | Plant
34 | Tender | FAVA Tender |  | Plant
35 | Tender | Pumps Tender | RC/PAT route | Plant
36 | Tender | Security Tender |  | Plant
37 | Tender | OWC Tender | Standardise and rate contract? | Project
38 | Tender | STP Tender | Space design by Safetreat type vendors shall be pro bono | Project
39 | Tender | WTP Tender | Standardise and rate contract? | Project
40 | Tender | Odour control Tender | Standardise and rate contract? | Project
41 | Tender | Pools Tender |  | Project | Arch paln section and pool type
42 | Tender | RWH Tender |  | Project
43 | Tender | DG Tender | RC/PAT route | Project
44 | Tender | PNG Tender |  | Project | 3RD PARTY TENDER
45 | Tender | Substation |  | Project
46 | VFCs | VFC - Plinth Level | incl Coordinated Drawing | Plant | 2 weeks after release of Architecture VFC'S | Architect
47 | VFCs | VFC - Basement Levels | incl Coordinated Drawing | Plant | 2 weeks after release of Architecture VFC'S | Architect
48 | VFCs | VFC - Podium Levels | incl Coordinated Drawing | Plant | 2 weeks after release of Architecture VFC'S | Architect
49 | VFCs | VFC - P0 or Ground | incl Coordinated Drawing | Plant | 2 weeks after release of Architecture VFC'S | Architect
50 | VFCs | VFC - Typical Levels | incl Coordinated Drawing | Plant | 2 weeks after release of Architecture VFC'S | Architect
51 | VFCs | VFC - Refuge Levels | incl Coordinated Drawing | Plant | 2 weeks after release of Architecture VFC'S | Architect
52 | VFCs | VFC - Service Level(s) | incl Coordinated Drawing | Plant | 2 weeks after release of Architecture VFC'S | Architect
53 | VFCs | VFC - Penthouse floors | incl Coordinated Drawing | Plant | 2 weeks after release of Architecture VFC'S | Architect
54 | VFCs | VFC - Terrace | incl Coordinated Drawing | Plant | 2 weeks after release of Architecture VFC'S | Architect